## Slide 1
JHBI
Quarterly Update
Where we are. What slipped. What's next.
OCEAN'S 13 EDITION · 13 PEOPLE · 1 AUDACIOUS PLAY
Mike Ames · Q2 2026 · Internal Team Working Session
Notes: Welcome. This is our quarterly working session. I want to be direct: we're behind on schedule by roughly two months, and I'll explain exactly why. But I also want to spend most of our time on what's working, what we're learning, and where we're going. We're a new group doing genuinely new things at Jack Henry — that comes with friction, and we'll talk through it together. Plan is roughly: demand story, MVP status, the honest truth on slippage, AI in our SDLC, a roundtable, then the vision. About an hour. Push back any time.

## Slide 2
AGENDA
JHBI Quarterly Update · Q2 2026
2 / 38
What we'll cover today
Roughly 60 minutes — discussion encouraged throughout
01
The demand story
Why JHBI matters and what the market is telling us
02
MVP at a glance
All five pillars and where each one stands
03
The honest truth
Where things slipped, why, and what we're doing about it
04
AI in our SDLC
Cursor, Opus, Sonnet — and best practices we're adopting
05
Team roundtable
Wins, blockers, and one thing we want to learn
06
The vision
What JHBI looks like 12 months from now
Notes: Six chunks. The first half is about progress and demand. The middle is the honest accounting of where we slipped. The back half is about how we work and where we're going. Hold questions if you can; otherwise jump in.

## Slide 3
MISSION BRIEFING
JHBI Quarterly Update · Q2 2026
3 / 38
MISSION BRIEFING · EYES ONLY
The Job.
Six months. Five pillars. Thirteen of us. One audacious play.
TARGET
The mark.
A fragmented data landscape inside Jack Henry. Six sources. No unified view. Growing market demand. We consolidate, modernize, and surface it.
THE CREW
Thirteen of us.
The only group at Jack Henry doing net-new modern cloud at this scale. We move fast, we ship clean, we own outcomes.
THE PLAY
MVP.
MVP demo-ready by end of Qx. First paying client by year-end. Become the reference pattern for the company in 12 months.
THE HEAT
What could blow it.
Scope. Source-team CDC pushback. The internal tax. We name the heat out loud so it can't surprise us.
Notes: Set the tone. We're going to talk about real, hard things today — slips, blockers, hard tech. Before we do, I want everyone aligned on what the actual job is. Read the four cards aloud — target, crew, play, heat. Tone-wise: this is the Ocean's 13 framing for the meeting. We're the only group at JH doing this. It's audacious, it's hard, and we are absolutely going to pull it off. Saul would be proud.

## Slide 4
TEAM
JHBI Quarterly Update · Q2 2026
4 / 38
WELCOME
Candi Westin
Newest member of the JHBI team — we're 13.
Round of welcome
Mic goes around. One word each.
Everyone says one word that captures what we're about as a team — what we want Candi to feel walking in. Candi goes last and gets the floor for ~60 seconds: who you are, what brought you here, anything we should know.
Candi Westin
[ AI/ML Data Engineer]
JOINED
[ Last Monday ]
WORKING ON
[ Data Science AI/ML Stuff ]
FUN FACT
Knows Lewis
Notes: Welcome Candi properly. Format: I'll go around the room and each person says ONE WORD that captures what we're about. Quick — no speeches. Then Candi gets the floor for about 60 seconds. Reminder for the room: Candi joining means we're 13 now. Bring her into the chat threads, the Slack channels, the working sessions. Don't make her ask. Fill in role / team / fun fact in this slide before the meeting if you want — or leave the brackets and improvise.

## Slide 5
TEAM
JHBI Quarterly Update · Q2 2026
5 / 38
Birthdays we missed
We owe you cake. Filing this under things we won't let happen again.
[ Name ]
[ Date ]
Cake at next team lunch.
[ Name ]
[ Date ]
Cake at next team lunch.
[ Name ]
[ Date ]
Cake at next team lunch.
[ Name ]
[ Date ]
Cake at next team lunch.
Going forward: 13 people on the team. ~3–4 birthdays per quarter on average. Calendar reminder going up this week so we celebrate them in real time, not in apologies.
Notes: Quick acknowledgment, not a long thing. Read each name aloud, brief 'happy belated birthday' from the room. Then state the going-forward plan: shared team calendar with birthdays, recurring monthly reminder, cake at the team lunch closest to the date. Fill in the four cards before the meeting — names and dates. If you missed more than four, add slots; if fewer, leave blank slots empty (just delete the cards in PowerPoint).

## Slide 6
THE CREW
JHBI Quarterly Update · Q2 2026
6 / 38
Meet the Thirteen
Same crew, same play — now with one more. Real names go where the brackets are.
The Brain
[ Real name ]
architecture
The Hacker
[ Real name ]
backend & data
The Inside Man
[ Real name ]
security · PCI
The Wheelman
[ Real name ]
CI/CD · DevOps
The Pickpocket
[ Real name ]
ingestion · CDC
The Locksmith
[ Real name ]
auth · RBAC
The Money
[ Real name ]
BI & reports
The Charm
[ Real name ]
portal · UX
The Cleaner
[ Real name ]
data quality
The Grifter
[ Real name ]
GTM · CU presentations
The Lookout
[ Real name ]
observability
The Mastermind
[ Real name ]
PM · strategy
The Wildcard
Candi Westin
Candi · newest
Notes: Crew reveal. Read each code name aloud, then pause for the real name (or improvise — half the fun is everyone arguing about who's The Pickpocket). Before the meeting: fill in real names in the brackets, optionally rename code names — these are just starters. Candi's already pinned to The Wildcard in amber. Heist references encouraged: 'You shake Sinatra's hand, you stand up like a man.' 'Are you in or are you out?' Etc.

## Slide 7
01
The demand
is real.
And it's louder than we expected.
Notes: I want to start with demand because it sets the table. Before we talk about what we built or where we're behind, I want everyone in this room to feel what the market is telling us. We're not pushing JHBI uphill. The pull is there.

## Slide 8
DEMAND
JHBI Quarterly Update · Q2 2026
8 / 38
Demand by the numbers
Four signals from the last 90 days
~200
Attendees at our first JHBI webinar
100+
Pre-registrants for our next webinar
~200
Across two CU presentations delivered
25
jhaKnow new sales YTD — adjacent demand
Net-net: people are showing up to learn, asking to be on the next call, and buying in adjacent products. The pipeline of attention is real.
Notes: Webinar one packed the room. Webinar two already has more than 100 people pre-registered before we've sent the second push. Two CU presentations, ~100 in each room. And jhaKnow — adjacent product, similar buyer — has 25 new sales this year. I don't have a single demand signal pointing the wrong direction. That matters because everything else we'll talk about today gets easier when the market is pulling.

## Slide 9
DEMAND · DEEP DIVE
JHBI Quarterly Update · Q2 2026
9 / 38
WEBINAR #1
A deeper look.
Who showed up, what they asked, what we learned.
~200
Attendees
[ XX% ]
Engagement / stayed to end
[ X ]
Demo requests follow-up
Insert detailed webinar stats deck here · registrations, attendance curve, top questions, follow-up actions
Notes: Transition slide into your detailed webinar stats deck. Fill in the engagement % and demo-request count if you want a teaser before the deeper dive — or delete the brackets and let your follow-on deck do the work. Hand-off line: 'On the prior slide we said ~200 — let me show you what that ~200 actually looked like.' Then jump to your stats deck. When that's done, return to this deck on the 'What this means for us' slide.

## Slide 10
DEMAND
JHBI Quarterly Update · Q2 2026
10 / 38
What this means for us
Three implications worth internalizing
We are not a science project
There is a buyer waiting. The work we ship in the next two quarters has a direct line to revenue and retention conversations our colleagues are already having.
Speed compounds
The faster we land MVP, the more webinars, demos, and CU conversations have a real product to point at — instead of a deck.
Quality is non-optional
The audience is bankers, payments people, and risk officers. First impression decides whether JHBI is taken seriously inside Jack Henry and outside.
Notes: Three takeaways I want every person here to leave with. We're not building speculatively. Speed and quality both matter — they're not in tension when we're disciplined.

## Slide 11
02
MVP
at a glance.
Five pillars. One platform. One credible end-to-end demo.
Notes: This is the scope frame. MVP is not 'everything we want eventually'. It's the smallest credible end-to-end story we can put in front of a buyer.

## Slide 12
MVP OVERVIEW
JHBI Quarterly Update · Q2 2026
12 / 38
The five pillars of MVP
Each one has to land for the demo to feel real
01
Contractor Onboarding
Get the right hands on keyboards
02
Infrastructure
GCP projects, Azure PowerBI, CI/CD
03
Self-Service Portal
RBAC, embedded reports, AI query, pipeline status, Alation
04
Backend & Data
6 payment sources, CDC, tokenization, medallion
05
Visualization
10 PowerBI reports the buyer actually sees
Notes: Five pillars. We'll walk each one with a status. Then I'll be honest about where we slipped.

## Slide 13
HIGHLIGHTS
JHBI Quarterly Update · Q2 2026
13 / 38
What we shipped this quarter
The wins worth naming out loud
GCP foundation stood up
Sandbox, Data, Compute, PCI projects exist with org policies, budgets, and IAM scaffolding
First contractors productive
Onboarded core team and they are now committing to repos, not waiting on access
CDC framework prototyped
Debezium pattern proven against a first source — we know it works
Tokenization API path
Sensitive-data handling pattern selected, sketched, and reviewed with security partners
Portal scaffold live
RBAC + embedded PowerBI shell working end-to-end in dev
JHBI brand traction
Two webinars, two CU rooms, ~500 humans engaged with the JHBI story
Notes: Real progress that doesn't get talked about enough. I wanted these on a single slide so the team sees them collected. None of these were free — they took real work.

## Slide 14
TIMELINE · H1
JHBI Quarterly Update · Q2 2026
14 / 38
Where the work landed: Jan → Jun 2026
What we ran, what shipped, what slipped, what's still in flight
Jan
Feb
Mar
Apr
May
Jun
Contractor onboarding (slipped ~6wks)
GCP core projects: Sandbox / Data / Compute
GCP PCI + shared / utility projects
Azure / PowerBI tenant + workspaces
CI / CD pipelines (IaC, services, dbt)
Portal: RBAC + embedded PowerBI
Portal: AI query builder + pipeline page
CDC framework (Debezium) + tokenization
First payment source CDC prototype
PowerBI: 4 of 10 reports in design
TODAY
Demand events
Webinar #1 (~200)
CU presentations ×2
Webinar #2 (100+ pre-reg)
Done
In progress
Slipped
Planned
Milestone
Notes: This is the lived reality of H1. Onboarding is the long amber bar — that's the slip. Green bars (GCP core, Azure/PowerBI, CI/CD, Portal RBAC + embedded) are done. Teal bars are in flight and on track. The amber today line shows where we are right now. The dots at the bottom are demand events — what the market saw of us during this period. Notice they're real and recent: a webinar landed, two CU rooms, second webinar already pre-registered.

## Slide 15
PILLAR 01 — ONBOARDING
JHBI Quarterly Update · Q2 2026
15 / 38
Contractor Onboarding
The unglamorous pillar that gates everything else
Status
Recovering
Slow start.
Background checks, system access, and laptop logistics ran weeks long
Single biggest contributor to our two-month slip
Most contractors are now productive — past the worst of it
We will not repay this tax in Q3
What's next
Lock the playbook. Don't repay the tax.
Document the onboarding runbook end-to-end (access, repos, secrets, tooling)
Pre-stage GCP IAM and PowerBI workspace access at offer-accept
First-week checklist: commit on day 3, demo on day 10
Named owner: PM + EM pairing; review monthly until friction is gone
Notes: I'll just say it: onboarding contractors took roughly two months longer than I planned for. Some of that is being a new group — we didn't have a paved road. Some is the reality of secure-environment access at a regulated company. What I will not accept is repaying the same tax next quarter. We're writing the runbook now.

## Slide 16
PILLAR 02 — INFRASTRUCTURE
JHBI Quarterly Update · Q2 2026
16 / 38
Infrastructure
GCP projects, Azure PowerBI, CI/CD — the substrate
GCP project layout
Sandbox
live
Data
live
Compute
live
PCI
in progress
Shared / others
in progress
Azure / PowerBI
Tenant + capacity provisioned
Workspace topology defined (dev / test / prod)
Embedded auth pattern proven against portal
Row-level security pattern in design
CI / CD
Pipelines for IaC, services, and dbt models
Branch protection + required reviews on day one
Secret scanning and SBOM in baseline pipeline
Promotion: dev → test → prod with manual gate
Open risk
PCI scope review
Final PCI project boundary and control mapping is the long-pole. Active with security partners. Targeting next sprint.
Notes: Three projects are live and useful. PCI and the shared/utility projects are mid-flight. Azure and PowerBI: tenant, capacity, and workspaces are real; embedded auth works against the portal. CI/CD pipelines are baseline-good — IaC, services, dbt — with secret scanning. The honest open risk is PCI scope. We're working it.

## Slide 17
PILLAR 03 — PORTAL
JHBI Quarterly Update · Q2 2026
17 / 38
Self-Service Portal
Where the buyer actually touches JHBI
User mgmt + RBAC
LIVE
AD-backed, role model defined, audit log
Embedded PowerBI
LIVE
Auth flow + workspace mapping working
AI-assisted query builder
IN PROGRESS
NL → SQL prototype against silver layer
Pipeline status page
IN PROGRESS
Surface ingestion + dbt run health
Alation data catalog
DESIGN
Catalog model + first sources mapped
Notes: Portal is the surface the buyer touches. RBAC and embedded PowerBI are working. AI query builder is the most exciting piece — NL to SQL against the silver layer, prototype is live, polishing for the demo. Pipeline status page is mid-flight. Alation is in design — catalog model and first sources mapped.

## Slide 18
PILLAR 04 — BACKEND
JHBI Quarterly Update · Q2 2026
18 / 38
Backend — six sources of payment data
All roads lead to the medallion
iPay Solutions
discovery
PayCenter
discovery
Payrailz Platform
CDC prototype
Enterprise Payment Solutions (EPS)
design
Jack Henry Wires
design
JHA SmartPay Platform
discovery
Heads up: We've gotten genuine pushback on CDC against a couple of these sources. We're working source-by-source rather than fighting a platform-wide battle. More on the next slide.
Notes: Six sources for MVP. One has a working CDC prototype. Two are in active design. Three are in discovery. We have real CDC pushback from a couple of source teams — concerns about replication load, ownership, audit trail. We're handling it source-by-source rather than trying to win one big architecture argument.

## Slide 19
PILLAR 04 — BACKEND
JHBI Quarterly Update · Q2 2026
19 / 38
Ingestion, sensitive data, and the medallion
How payments data lands and matures
CDC — Debezium framework
Source-agnostic connector pattern
Schema registry + replay-from-offset
Per-source onboarding playbook (auth, load, ownership)
First source in prototype — pattern proven
Pushback acknowledged; working with each source team individually
Tokenization API
Sensitive fields tokenized at landing
Reversible tokens behind PCI project boundary
Hashing pattern for join-keys outside PCI
Designed with security partners — under review
Test data path uses synthetic values end-to-end
Medallion architecture
Bronze
raw, immutable
Silver
conformed, joinable
Gold
business-ready marts
Platinum
curated, exec-ready
Notes: Three things to internalize. First, our CDC framework is real — not a slide. Second, sensitive data has a designed home: tokenized at landing, reversible behind PCI, hashed outside. Third, the medallion gives us a shared vocabulary — bronze raw, silver conformed, gold business-ready, platinum exec-ready. Test data management runs alongside this — synthetic values let us demo and develop without prod sensitive data.

## Slide 20
PILLAR 05 — VISUALIZATION
JHBI Quarterly Update · Q2 2026
20 / 38
Visualization — 10 PowerBI reports
What the buyer actually sees
Payment volume
design
Transaction success
design
Channel mix
design
Fee + interchange
discovery
Settlement timing
discovery
Risk + exceptions
discovery
Customer cohorts
discovery
Wires throughput
discovery
SmartPay adoption
discovery
Exec scorecard
design
Heuristic: if a report doesn't show up in a CU conversation, it doesn't ship in MVP. We'd rather have 6 great reports than 10 mediocre ones.
Notes: Ten reports planned. Four in active design — the ones we know land in every CU conversation. Six in discovery. I'd rather ship six great reports than ten mediocre ones, and we'll prune based on what real conversations call for.

## Slide 21
03
The honest
truth.
We're roughly two months behind. Here's why — and what we're doing.
Notes: I don't want anyone to leave this room thinking we're hiding it. We're behind, I know it, and I want to walk through why.

## Slide 22
HONEST TRUTH
JHBI Quarterly Update · Q2 2026
22 / 38
Why we're ~2 months behind
Three causes, ranked by impact
1
Slow contractor onboarding
Background checks, access provisioning, and laptop logistics took weeks longer than planned. This is the biggest single contributor.
~6 weeks
2
Infrastructure ramp-up cost
Standing up GCP project structure, org policies, IAM, and PCI scoping at a regulated company is genuinely heavy lift the first time. We're now past most of it.
~3 weeks
3
CDC pushback on data sources
Source teams have legitimate concerns about replication load, ownership, and audit. We're working source-by-source, but it adds calendar time.
~2 weeks
Context: We're the only group at Jack Henry doing net-new modern-cloud work at this scale. Some of this tax is one-time and we're paying it once.
Notes: Three causes. Ranked. Onboarding is the big one. Infra ramp-up is real but mostly done. CDC is friction we're working through with the source teams. I want to name the context: we are the only group doing net-new modern-cloud work at this scale at Jack Henry. Some of this is unavoidable first-mover tax.

## Slide 23
HONEST TRUTH
JHBI Quarterly Update · Q2 2026
23 / 38
What we're doing about it
Six concrete actions in the next 30 days
Onboarding runbook
Lock the playbook so we don't repay the tax in Q3
Pre-staged access
GCP IAM and PowerBI roles created at offer-accept, not day-one
Source-by-source CDC plan
Named owner per source, weekly working session
PCI scope close-out
Final boundary + control mapping with security partners
MVP pruning
Cut anything not on the demo critical path
Weekly slip review
Visible burn-up on shared dashboard — no surprises
Notes: Six actions, each with an owner, each in the next 30 days. The single most important one is the onboarding runbook — we will not pay that tax twice. Pruning is also important: anything not on the demo critical path comes out for now and goes into the post-MVP backlog.

## Slide 24
04
AI in our
SDLC.
Cursor + Opus + Sonnet — and the practices that make it real leverage.
Notes: Now to the part that's most fun and most consequential. We have access to a serious AI stack. Most teams don't yet have a shared playbook for using it well. We're going to build one.

## Slide 25
AI SDLC
JHBI Quarterly Update · Q2 2026
25 / 38
Our AI stack today
What's in our hands — and what each tool is for
IDE
Cursor
Inline completion + agentic edits
Multi-file refactors
Repo-aware chat with @file / @symbol
Where most of our coding happens
HARD REASONING
Opus
Architecture and ambiguous specs
Security and data-model reviews
Gnarly debugging when stuck
Reach for it when stakes are high
DAILY DRIVER
Sonnet
Most code generation and tests
SQL and dbt model authoring
Doc writing, summaries, prompts
Fast pair-programming partner
Notes: Cursor is our IDE. Opus is the hard-reasoning model — pull it in for architecture, ambiguous specs, gnarly debugging, security and data-model reviews. Sonnet is the daily driver — most code generation, tests, SQL, doc writing. The mistake people make is using one model for everything. Pick the right tool for the cognitive lift.

## Slide 26
AI SDLC
JHBI Quarterly Update · Q2 2026
26 / 38
Best practices we're adopting
Six habits that turn AI from a toy into leverage
Right model for the lift
Sonnet for most work. Opus when stuck, ambiguous, or stakes are high (architecture, security, data model, gnarly debug).
Spec before code
Write the prompt like a small PRD: goal, inputs, constraints, acceptance criteria. The clearer the spec, the better the output — same as humans.
Never trust, always verify
Tests, types, code review. AI hallucinates plausible code. Treat its output like a confident junior — read every line.
Repo-aware context
Use Cursor's @file / @symbol so the model sees the real codebase. Cut-paste blind prompts produce blind code.
Capture the prompts that work
Shared prompt library in the repo. Treat winning prompts as artifacts — version them like code.
AI-aware review etiquette
Be explicit when a PR was AI-assisted. Reviewers know to look harder for plausible-but-wrong patterns.
Notes: Six habits I want this team to adopt. The two most underrated: spec before code, and capture the prompts that work. If you write a prompt that produces something genuinely good, that prompt is an artifact — version it, share it. Also: be honest in PRs when something is AI-assisted. It calibrates how reviewers read it.

## Slide 27
05
Roundtable.
Microphone moves around. Everyone gets one.
Notes: This is the part where I shut up. Mic goes around. We'll do four prompts — quick, ~30 seconds each.

## Slide 28
ROUNDTABLE
JHBI Quarterly Update · Q2 2026
28 / 38
Four prompts. Mic goes around.
Keep it to ~30 seconds — we want everyone in
Brag
What's one thing you shipped or figured out this quarter that you're quietly proud of?
WTF moment
What was the most ridiculous blocker, bug, or process moment? (No names, just the story.)
Shout-out
Brag about someone else on the team. Specific is better than vague.
Want to learn
One thing — technical or otherwise — you want to learn or get better at next quarter.
Notes: Four prompts. Brag, WTF, shout-out, want-to-learn. Mic goes around. About 30 seconds each. Bonus rule: if you steal someone else's answer, you owe them coffee.

## Slide 29
06
The vision.
Where JHBI goes from here.
Notes: Last section. I want everyone to leave knowing where this is going — not just what's next sprint.

## Slide 30
VISION
JHBI Quarterly Update · Q2 2026
30 / 38
Where we are in 12 months
JHBI as the modern-cloud reference implementation at Jack Henry
NOW → 90 DAYS
Land MVP
All 5 pillars demo-ready. 6 great PowerBI reports. First credible end-to-end CU walkthrough. Onboarding tax paid once and only once.
90 → 180 DAYS
Scale the demo into deals
Repeatable CU + buyer flow. Catalog adoption. AI query builder graduates from demo to real usage. Real customer telemetry on the platform.
180 → 365 DAYS
Become the reference
JHBI is the answer when someone at Jack Henry asks 'how should we do net-new cloud + data?' Pattern is documented, paved-road, copyable.
Notes: Three horizons. 90 days, 180 days, 365 days. The frame I want everyone to hold: in 12 months, when someone at Jack Henry asks 'how should we do net-new modern cloud and data?' the answer is JHBI. Not because we won an argument — because the pattern is documented, paved-road, and copyable.

## Slide 31
VISION
JHBI Quarterly Update · Q2 2026
31 / 38
What 'we made it' looks like
Concrete enough to know when we got there
A buyer says yes
Because of what they saw, not who they know — JHBI closes its first deal driven by the demo itself.
An engineer copies us
Another team at Jack Henry adopts our paved road — repo template, pipelines, CDC pattern, medallion.
A customer queries themselves
A real CU user opens the portal, asks a question in plain English, and gets a useful answer without us in the loop.
The runbook holds
We onboard the next contractor in days, not weeks. No re-paying the tax.
Our team wants to stay
People who are hard to keep tell us this is the best work they've done.
Notes: Five concrete success indicators. I deliberately picked things you'll be able to point at and say 'that happened' or 'that didn't'. If three of these five are true in 12 months, I'm going to call this a hit.

## Slide 32
TIMELINE · H2
JHBI Quarterly Update · Q2 2026
32 / 38
What's next: Jul → Dec 2026
The operational plan behind the 12-month vision
Jul
Aug
Sep
Oct
Nov
Dec
Onboarding runbook + paved-road docs
PCI scope close-out + security sign-off
Portal: AI query GA + Alation rollout
Backend: PayCenter + EPS integrations
Backend: Wires + SmartPay integrations
Backend: iPay (final source)
PowerBI: remaining 6 reports built
MVP launch — first end-to-end CU demo
Customer telemetry + feedback loop
Reference pattern: docs + paved road
Demand events
Q3 webinar
Industry conference
Year-end CU summit
Done
In progress
Slipped
Planned
Milestone
Notes: Six months. Ten work streams. One milestone — the first end-to-end CU demo in early September. I've sequenced backend work source-by-source so we don't fight every team at once. Reference-pattern documentation comes at the end on purpose — we want it written from the real shape of what we built, not what we planned. Three demand events anchor the half: a Q3 webinar, an industry conference, and a year-end CU summit. If we hit the milestone in September, the back half of this Gantt becomes the easiest selling we'll ever do.

## Slide 33
ASKS
JHBI Quarterly Update · Q2 2026
33 / 38
What I'm asking from this room
Three things that compound
01
Speak up early
If you see a slip, a risk, or a dumb pattern — surface it the same week. Don't carry it. Slack me, raise it, kill it early.
02
Steal each other's work
Prompts, snippets, runbooks, infra patterns. If you wrote it once, share it so no one else writes it again.
03
Show up for the demo
Every webinar, every CU conversation — that's where our work meets the market. If you can be in the room, be in the room.
Notes: Three asks. Speak up early. Steal each other's work. Show up for the demo. Each of these compounds. We get a multiplier from a team that does these consistently.

## Slide 34
Thank you.
We are doing something hard. We are doing it well.
Questions, pushback, ideas — open floor.
CREW DISMISSED · SAME TIME, NEXT QUARTER
Notes: Open the floor. No question is too small or too obvious. If something didn't make sense, that's on me, not you. Push back, propose, ask. Ocean's 13 closer (optional): 'You shake Sinatra's hand, you stand up like a man.' Or just: 'Crew dismissed. See you next quarter.'

## Slide 35
APPENDIX
Team games.
Three quick activities. Pick one as a warm-up, drop one into the roundtable, save one for the close.
01
JHBI Pictionary
10 min · 2 teams
02
Worst Possible Name for JHBI
5 min · pairs
03
Quarter in Six Words
5 min · round robin
Notes: Three games. Use them however you want. Pictionary is the loudest — best as a warm-up if the room feels tense. Worst Name is the silliest — works as a palate cleanser between honest-truth and AI SDLC. Six Words is the most reflective — best as the closer right before Thank you.

## Slide 36
APPENDIX · GAME 01
JHBI Quarterly Update · Q2 2026
36 / 38
JHBI Pictionary
Watching someone try to draw row-level security is its own reward
TIME
10 minutes
FORMAT
Two teams
MATERIALS
Whiteboard + marker (or shared screen)
How to play
1. Split the room into two teams. Doesn't have to be even — bigger team gets harder terms.
2. Each round: one person from a team draws a term pulled from the hat.
3. 60 seconds. No words. No letters. No numbers. No symbols (no = signs, no arrows with labels).
4. Either team can shout the answer. First correct guess wins the point.
5. Alternate which team's drawer is up. Best of 6 rounds. Loser buys coffee.
Pull from the hat
Tokenization API
Medallion architecture
Row-level security
Source-by-source CDC
Embedded PowerBI report
PCI compliance scope
Debezium connector
AI-assisted query builder
Pipeline status page
Alation data catalog
Onboarding runbook
Schema registry
Notes: Print these terms on slips of paper, fold, drop in a hat or coffee mug. House rule: drawers can use any number of distinct shapes but can't use words or letters. If neither team gets it in 60 seconds, both teams lose the point. Watch the energy in the room — call it after 6 rounds even if you have time for more.

## Slide 37
APPENDIX · GAME 02
JHBI Quarterly Update · Q2 2026
37 / 38
The Worst Possible Name for JHBI
Pure dumb fun — energizes the room before the serious bits
TIME
5 minutes
FORMAT
Pairs, then full-room vote
MATERIALS
Index cards + pens
How to play
1. Pair up. Strangers > friends. Couches > tables.
2. 90 seconds: come up with the most painfully bad rebrand for JHBI. The worse the better.
3. Each pair reads their best one out loud. No commentary, just the name.
4. Group vote: everyone raises a hand for the worst (= best). Tie? Run-off.
5. Winner gets a printed certificate. Or just bragging rights until next quarter.
Inspiration (use sparingly)
PayBro
tech bro energy, banking misread
MoneyHenry
feels like a sandwich shop
The CashCanal
menacing yet wet
JackBank.io
domain squatter chic
Henrify
verbing what should not be verbed
BankBuddy 2.0
the 2.0 is doing all the work
Notes: Read the room before sharing inspiration — sometimes it suppresses creativity. If pairs are stuck, the unlock is usually 'lean into the worst possible vibe' (Web3 finance bro, mid-2000s portal, tax software). Save the winners. They're surprisingly useful as cold-open jokes in future stakeholder updates.

## Slide 38
APPENDIX · GAME 03
JHBI Quarterly Update · Q2 2026
38 / 38
Quarter in Six Words
Hemingway-style. Exactly six. Goes fast. Stays with you.
TIME
5 minutes
FORMAT
Round robin — everyone, no skips
MATERIALS
None (or one shared doc to capture)
How to play
1. Each person summarizes the entire quarter in exactly six words. Not five. Not seven.
2. 30 seconds of silent thinking. Then mic goes around. No skipping.
3. No commentary between answers. Just listen. Resist the urge to react.
4. Designated scribe types every answer into a shared doc as people speak.
5. Best as the closer — right before the Thank you slide.
Examples to set the tone
"Built a lot. Slept too little."
"PCI scoping aged me ten years."
"Onboarding hell. Then everything else worked."
"Debezium said no. Then said yes."
"Webinars more popular than expected, honestly."
"Behind on schedule. Ahead on demand."
Notes: Strict on the word count — six exactly. Forces precision. Don't react between answers; let them sit. The scribe is essential — write everything down because the gold lines are unpredictable. Read the top three at the start of next quarter's update as a callback.